## Sheet1
Ticket | Ticket Comment | Version | Text for Future Updates page
TEDEPO-1223 | present and decide on terms refactoring | ePO core development 4.0.0Assignee: Eugeniu Costetchi
TEDEPO-1040 | Prepare final draft of eContract | CM-3.2.0.betaeContract module developmentP
TEDEPO-891 | Modeling procedure and subprocedure | CM-4.0.0.betaePO core development 4.0.0P3w
TEDEPO-962 | Mappings requirements standard forms | CM-3.2.0.betaePO core development 3.2.0P2w
TEDEPO-1039 | Present final draft of eContract | CM-3.2.0.betaeContract module developmentP2h
TEDEPO-905 | Harmonize homogenous information structure across modules | CM-3.2.0.betaeOrdering module updates 3.2.0P2d
TEDEPO-1133 | Fix model2owl errors in ePO_CM.eap | ePO core development 3.2.0A
TEDEPO-985 | Add simple definitions for relations between classes (where needed) | CM-3.2.0.betaePO core development 3.2.0A3d
TEDEPO-949 | revise NEW eForms BTs and ensure coverage in ePO | CM-3.2.0.betaePO core development 4.0.0A1w
TEDEPO-918 | WP 1.1 Update UML conventions | CM-3.2.0.betamodel2owl doc updatesAssignee: Eugeniu Costetchi 2w 1d
TEDEPO-975 | Ontology metadata property should be made more complete | ePO core development 4.0.0V
TEDEPO-1159 | Renaming 'epo-cat:ItemDescription' to 'epo:ItemProperty’.​ | eOrdering module updates 3.2.0Assignee: MURIC Natalie
TEDEPO-1208 | Associations definitions harmonization | ePO core development 4.0.0A
TEDEPO-1219 | Start the ontology release process on 14th of June | ePO core development 4.0.0P2w
TEDEPO-1090 | Review changes that affect the standard form mappings | ePO core development 3.2.0P
TEDEPO-998 | 3.1.0 eNotice html does not have a diagram folder like the other modules. | CM-3.2.0.betaDocumentation and governanceP
TEDEPO-976 | Ontology publication following FAIR principles | CM-4.0.0.betaePO core development 4.0.0V1w 2d
TEDEPO-1072 | analyze ePO concepts wit respect to upper level ontology | ePO core development 4.0.0A
TEDEPO-1050 | eAccess 1st draft | CM-4.0.0.betaeAccess module development2w
TEDEPO-1054 | eAccess 3rd draft | CM-4.0.0.betaeAccess module development2w
TEDEPO-1055 | Present 3rd draft eAccess | CM-4.0.0.betaeAccess module development1d
TEDEPO-1056 | eAccess 4th draft | CM-4.0.0.betaeAccess module development2w
TEDEPO-1057 | Present 4th draft eAccess | CM-4.0.0.betaeAccess module development1d
TEDEPO-1058 | eAccess 5th draft | CM-4.0.0.betaeAccess module development2w
TEDEPO-1059 | Present Final eAccess | CM-4.0.0.betaeAccess module development1d
TEDEPO-1209 | Renaming Objects in eNotice module | ePO core development 4.0.0A
TEDEPO-1158 | Standardized Namespace Prefix for ePO Model | ePO core development 4.0.0A
TEDEPO-1230 | Checking some modeling issues in ePo | ePO core release 4.0.0 (LTS)A